## Sheet1
|  |  |  | April |  |  |  |  | May |  |  |  | June
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
전체 | Related contents acquisition | April 8: Mid Demo; June 14: Final Demo
Implement Android GUI | bar: 3 to April 6; April 9 to May 13
Implement psychological analysis function | bar: 3 to April 6; April 9 to May 11
Implement writing psychological state function | bar: 3 to 4
Implement speech recognition function | bar: April 9 to May 10
Implement translation function | bar: May 11 to May 12
Implement log-in function & DB linking | bar: April 5 to April 6
Implement blood glucose level function & DB linking | bar: April 6; April 9
Implement medication administration function & DB linking | bar: April 9 to May 10
Implement diet management function & DB linking | bar: May 10 to May 11
Implement encryption function | bar: May 12 to May 13
Implement additional function | bar: May 12 to May 13
추가 기능 구현 및 테스트 | bar: April 6; May 13
장혁재 | Diary UI | April 8: Mid Demo; June 14: Final Demo
판매자용 로그인/가입 기능 구현 | bar: April 5 to April 6
가게 배치도 입력 UI 및 저장 기능 | bar: April 6; April 9
가게 사용 통계 뷰어 | bar: April 9 to May 10
가게 자동 배치 알고리즘 구현 | bar: May 10 to May 11
어 | bar: May 12 to May 13
현 | bar: May 12 to May 13
남근우 | 소프트웨어 설계 | April 8: Mid Demo; June 14: Final Demo
데이터베이스 설계 | bar: 4 to April 5
Blood glucose level function | bar: April 9
Medication administration tracking function | bar: April 9 to May 10
Diet management function | bar: May 10 to May 11
Implement encryption function | bar: May 12 to May 13
Implement additional function | bar: May 12 to May 13
조성욱 | 안드로이드 어플리케이션 UI 구현 | April 8: Mid Demo; June 14: Final Demo
Sentiment analysis function | bar: 3 to April 6; April 9 to May 11
Implement encryption function | bar: May 12 to May 13
Implement additional function | bar: May 12 to May 13